## Sheet1
MIS 311 Week 8 Assignment
Your Name here: | Ethan Dunzer
Part 1 : Explain the timing and purpose of key project documents, relating each to the Software Development Process Framework:
a. Project Vision | The Project vision is the is the all incompesing vision of what the project should represent at the start of the project. This envovles detailed information about the stakeholders, businesses problems and opportunities, solutions, and benefits for the business.
b. Statement of Work | The Statement of work is the document that is created after anaylsis of the project visision and therefore has a more detailed and defined representation of the project. This often includes The different activities, deliverables, and a timetable for the project making it the offical plan for the project.
c. Business Case | The Businesss case is the explanation of why a project was created or initiated. It represents a certain scenario that takes the project vision and anaylsis into account to convey the a plan of action for senior management and how it will effect the business.
d. Project Charter | The Project Charter is a more concise version of the Statement of work where all planning an execution are detailed efficently but all cost/benefit analysis is omitted. This typically happens later after the final project has been approved and refined.
Part 2 Mini case: Per the I2C2 embedded clinics/pharmacies (ECP) business case (page 509), I2C2 is considering a series of enhancements to this existing system. In planning discussions with I2C2 business and IT team members, the following points were captured in the meeting minutes. Complete the following for each of these points: (1) Determine if the item is a risk, and issue, an assumption, or a constraint. (2) For risks and issues, determine the level of impact (high, medium, or low) and relate it to a corresponding item in Table 12-2. (3) For risks, determine the level of probability (high, medium, or low) and your preferred mitigation strategy (avoidance, limitation, transference, or acceptance). For each item, explain your answers. Look for downdown selections in first three answer cells
Questions |  | 1 Type (select 1) | 2 If a risk or issue: determine level | 3 Preferred mitigation strategy | Explain your choices
1. Given the dozen countries in which I2C2 operates clinics/pharmacies, management decided to let three senior pharmacy leaders in Mexico, Ethiopia, and Malaysia be product owners on behalf of the rest of the world. |  | Risk | Medium | Transference | There are many potential issues by limited the leadership by 3 key personel that live in separate countries. This could create problems that would only be resolved through other parties | Risk | High | Avoidance
2. The prior point did raise a concern that those three leaders might not be able to speak for users in the other nine countries, given differences in legal regulations and market practices in different parts of the world. |  | Constraint |  |  | This is one of the potential problems that could happen so it becomes a possbile and likely constraint. | Issue | Medium | Limitation
3. Further, it was just determined that one of those three senior pharmacy leaders will be going out on paternity leave for two months. |  | Issue | Low | Transference | This is a current issue that will be resolved through transfering duties to other parties. | Assumption | Low | Transference
4. In discussing the “sharing drugs” feature, there was some disagreement regarding whether I2C2 pharmacies should be able to share drugs across national borders. In several geographically small countries in Central America, pharmacists noted that I2C2 pharmacies in different countries were only a few miles apart. The cost-estimation impacts of this could be large. |  | Risk | High | Limitation | This is a very large issue that could limit the ability to share drugs, and needs to be solved by localizing drugs into separate counties to limit the loss of funds by crossing boarders. | Constraint |  | Acceptance
5. For sharing drugs and consolidated purchasing, the system is currently built with each pharmacy running its own instance of the system using a local database. This will necessitate implementing a new architecture using a centralized database, either replacing the existing local databases or maintaining copies of that data. |  | Issue | Low | Acceptance | This is a current issue since the database will need to be changed in order for the project to start, it also needs to happen right away so acceptance of the increased cost will be the only way to deal with it.
6. The I2C2 team has historically underestimated the time and cost needed to develop features. Because of this, the CIO is requiring improved training on project estimation, planning, and management. |  | Risk | Low | Acceptance | This is a potential problem for the project and could change the timeline, and will have to be accepted in order for the project to continue.
7. Also, the CIO noted that I2C2 has historically utilized several key outside contractors, each of whom understands the I2C2 pharmacy system thoroughly. However, because I2C2 hasn’t used those contractors for almost a year, it is not clear if they will be available for this project |  | Assumption |  |  | This is an unknown problem and has not been confirmed, therefore it is an assumption and has no current issue or risk.
8. This project cannot start for another six weeks, while the development team finishes up another, unrelated project that is occupying them full-time. |  | Issue | Low | Acceptance | This is a current problem and is therefore an issue that has to be accepted since there are no alternatives.